# Weekly Status Submission Template

## Week Number: Week 1

## Date: 9/16/2026

## Student Name: Sara Yakubesan

## Original Plan for This Week: (5 points)

According to the project timeline submitted with my proposal, Week 1 goal was Literature Review and Finalize Research Design. The planned tasks were to complete a focused review of recent peer-reviewed literature related to corn yield and weather, review research on extreme-weather effects and crop yield prediction, identify defensible growing season periods and candidate extreme-weather indicators, and finalize the planned modeling and evaluation strategy. The goal for the end of the week was to establish the foundation of literature and overall research design that will guide the remainder of the project.

## Tasks Accomplished This Week: (10 points)

I completed the planned Week 1 research design work and also made progress on several tasks that were originally scheduled for later weeks in the project timeline.

The literature review was completed and used to finalize the major methodological decisions for the project. I created a Methodology Decision Table to document decisions related to the historical baseline, weather predictors, validation strategy, final evaluation period, performance metrics, and reproducibility. The historical baseline was finalized to include county identity, long-term temporal trend, and previous year county yield as the lag-1 yield predictor.

I also finalized the weather-feature definitions. Three fixed calendar windows were selected as literature-supported approximations of important portions of the corn growing season: May-June for early-season conditions, July for reproductive-critical period, and August-September for grain filling. Six conventional weather predictors were defined using mean temperature and total precipitation within these periods. Four extreme-weather indicators were also finalized: July hot-day count above 30°C, July accumulated heat above 35°C, longest July-August dry spell, and maximum May-July rolling 5-day precipitation.

In addition to finalizing the research design, I completed the weather-feature engineering workflow. The calculations were first tested and manually verified using the year 2000 before the process was expanded to the full 2000-2025 study period. The completed weather-feature dataset contains 2,392 county-year observations, representing all 92 Indiana counties across 26 years. All ten engineered weather predictors are complete with no missing values.

I then completed a development period audit of the engineered weather predictors using only 2000-2021 data so that the planned 2022-2025 final holdout period would not influence feature decisions. The audit supported retaining all four planned extreme-weather indicators. Severe heat above 35°C was relatively uncommon but was still observed in 287 of 2,024 development county years. The audit also identified a strong correlation between July mean temperature and July hot-day count, which will be evaluated for multicollinearity during later linear-model development.

## Comparison of Planned vs Actual: (10 points)

| Planned Task | Actual Progress |
| --- | --- |
| Complete a focused review of recent peer-reviewed literature related to corn yield and weather. | COMPLETED – The literature review was used to support decisions regarding weather timing, extreme-weather indicators, validation, and model comparison. |
| Review research on extreme-weather effects on crop yield prediction. | COMPLETED – The literature was used to define heat, dry-period, and heavy precipitation indicators. |
| Identify defensible growing-season periods and candidate extreme-weather indicators. | COMPLETED – Three fixed weather windows and four extreme-weather indicators were finalized and documented. |
| Finalize the planned modeling and evaluation strategy. | COMPLETED – The historical baseline, predictor groups, expanding-window validation strategy, 2022-2025 holdout period, performance metrics, and leakage safeguards were documented. |
| Additional progress beyond Week 1 plan | Historical data-quality assessment, historical-baseline preparation, weather-feature engineering, and development-period weather-feature audit were also completed or substantially advanced. |

In addition to completing the planned Week 1 tasks, I was able to make progress on several activities originally scheduled for later in the project timeline. Historical USDA and NOAA coverage and data-quality assessments, which were planned for Week 2, have already been completed. I also completed the weather-feature engineering and feature-audit work originally planned for Week 4 and made substantial progress on the historical baseline work planned for Week 5.

The final integration of the engineered weather features with the lag-1 modeling sample has not yet been completed, so I do not consider the Week 3 data-integration milestone finished. The original timeline places the full cleaning and integration process in Week 3.

## Self-Rating of Progress: (5 points)

- [ X ] Met the Planned Tasks

- [ ] Did Not Meet the Planned Tasks

I met the planned Week 1 tasks and completed portions of several later milestones. This places the project somewhat ahead of the original timeline in data-quality assessment, weather-feature engineering, and historical-baseline preparation while leaving additional time for data integration, model development, and troubleshooting.

## Plan for Next Week: (5 points)

Next week I plan to integrate the validated weather features with the lag-1 historical modeling sample and confirm the common county-year analysis set that will be used for model comparison.

The main tasks planned for next week are:

- Merge the engineered weather features with the historical yield modeling sample using the county FIPS and year.

- Verify the final common modeling sample and document any county-years excluded because lag-1 yield is unavailable.

- Construct the three planned predictor groups:

  - Historical baseline

  - Historical baseline plus conventional weather

  - Historical baseline plus conventional and extreme-weather predictors

- Confirm that all three predictor groups use identical observations and validation years.

- Evaluate multicollinearity in the linear model predictor sets, particularly the strong relationship identified between July mean temperature and July hot-day count.

- Begin preparing the expanding-window rolling-origin modeling workflow for subsequent model development.

This work will connect the completed feature-engineering stage to the model-development phase while maintaining the time-aware validation and holdout strategy established during Week 1.

## Evidence of Tasks Completed: (15 points)

Supporting evidence for the work described below is available in my GitHub thesis repository:

Sara Yakubesan_GitHub_Repository

Week 1 supporting figures and summary outputs are organized in the evidence/week_01 folder. The repository also contains the current Methodology Decision Table, project documentation, and reproducible R scripts used for historical-baseline development, weather-feature engineering, and feature auditing.

Evidence of the work completed this week includes:

- Methodology Decision Table documenting the finalized research-design decisions, including the historical baseline, weather-feature definitions, validation strategy, evaluation period, metrics, and reproducibility safeguards.

- Feature Definitions worksheet documenting the three weather windows, six conventional weather variables, four extreme-weather indicators, and alternatives that were considered but excluded.

- 07_usda_coverage_audit.R evaluating county-year availability and completeness of USDA corn-yield observations.

- 08_noaa_coverage_audit.R evaluating NOAA daily weather coverage, missing values, duplicate records, and county/date completeness for 2000–2025.

- 09_yield_history_availability_audit.R evaluating the availability of historical yield features.

- 10_historical_baseline_comparison.R comparing candidate recent-yield representations using expanding-window validation.

- 11_historical_baseline_setup.R creating the final lag-1 development sample and auditing the planned rolling validation folds.

- 12_weather_feature_engineering.R creating the six conventional and four extreme-weather predictors from daily NOAA observations.

- 13_weather_feature_audit.R evaluating feature distributions, severe-heat availability, moisture extremes, and predictor correlations using pre-2022 development data.

- indiana_weather_features_2000_2025.csv and indiana_weather_features_2000_2025.rds, containing 2,392 county-year observations across all 92 Indiana counties from 2000–2025 with no missing values in the ten engineered weather predictors.

- Weather-feature audit outputs, including the development feature summary, yearly severe-heat summary, predictor correlation matrix, high-correlation review, and extreme-weather audit results.

- The development-period audit confirmed complete 2000–2021 weather-feature coverage for 2,024 county-year observations while keeping the 368 observations from 2022–2025 separate as the final holdout period.